## Sheet1
Issue Log
Issue # | Issue Description | Impact on Project | Date Reported | Reported By | Assigned To | Priority(M/H/L) | Due Date | Status | Date completed | Comments
1 | Less options for user design in Java | Difficult to make the project presentable | 2020-10-04 | Decen Ng | Decen Ng | H | 13/04/2020 | Completed - Decided to use HTML for ease of design | 13/04/2020
2 | No knowledge of PHP system | No database system | 2020-10-04 | Deceng Ng | Decen Ng | H | 2020-01-05 | Completed- Used online tool to learn and crate a basic functioning prototype | 25/04/2020 | Have a working database
3 | Unfamiliar with the proposed Change request | Might not be able to meet the change proposed change request's requirements | 30/4/2020 | Jing Xian Ching | Jing Xian Ching | H | 17/5/2020 | Completed- Proposed change request was succesfuly implemented | 17/05/2020
4 | Communication among the programmers was lacking | Might not be able to fulfil system requirements on time | 30/4/2020 | Jing Xian Ching | Jing Xian Ching | H | 30/4/2020 | Completed- Programmers have discussed about what went wrong between their communication | 30/4/2020