## Sheet1
Cost Baseline
Project Name: UoW room booking system |  |  |  |  | Date: 1/5/2020
Note: Enter your WBS and costs each month. Add/delete rows and columns as needed and check all formulas (bolded below).
Week
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | Total Cost
WBS Categories
1 Project Preparation Phase
1.1 Interview Users | 240 | [7 empty] | 240
1.2 Compile Requirement | 120 | [7 empty] | 120
1.3 Project Charter Proposal and Approval | 40 | [7 empty] | 40
2 Project Planning phase | [8 empty] | 0
2.1 Scope statement | 120 | [7 empty] | 120
2.2 Cost management plan |  | 240 | [6 empty] | 240
2.3 Human resource Plan |  | 240 | [6 empty] | 240
2.4 Project Scheduling |  | 360 | [6 empty] | 360
2.5 Risk management plan |  |  | 240 | [5 empty] | 240
3 Design Phase | [8 empty] | 0
3.1 design UI |  |  |  | 600 |  |  |  |  | 600
3.2 Learning of PHP |  |  |  |  | 360 |  |  |  | 360
3.3 Design Database |  |  |  |  | 240 |  |  |  | 240
4 Testing phase | [8 empty] | 0
4.1 Test UI design | [6 empty] | 240 |  | 240
4.2 Test Backend | [6 empty] | 240 |  | 240
5 Presentation Phase | [8 empty] | 0
5.1 Prepare video for presentation | [7 empty] | 240 | 240
5.2 Rehearse for presentation | [7 empty] | 240 | 240
6 Change Request | [8 empty] | 0
6.1 Updating of scope statement | [5 empty] | 120 |  |  | 120
6.2 Updating of cost planning | [5 empty] | 120 |  |  | 120
6.3 Updating of HR planning | [5 empty] | 120 |  |  | 120
6.4 Updating of other documentations | [5 empty] | 240 |  |  | 240
6.5 Designing of system administration | [5 empty] | 360 |  |  | 360
6.6 Testing of System administration | [6 empty] | 240 |  | 240
Subtotal | 520 | 840 | 240 | 600 | 600 | 960 | 720 | 480 | 4960
Reserves*
Total | [8 empty] | 4960