## Sheet1
Cost Estimate
Project Name: | UoW room booking system |  |  |  |  | Date: 3/4/2020
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
| Internal | $/day | Internal | External | $/week | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Project preparation phase
1.1 Interview users | 10 | 40 | 400 | - | - | - | 400 |  | 400
1.2 Compile requirement | 6 | 40 | 240 | - | - | - | 240 |  | 240
1.3 Project Charter proposal and approval | 1 | 40 | 40 | - | - | - | 40 |  | 40
2 Project planning phase | [8 empty] | 0
2.1 Scope statement | 35 | 40 | 1400 | - | - | - | 1400 |  | 1400
2.2 Cost management plan | 30 | 40 | 1200 | - | - | - | 1200 |  | 1200
2.3 Human resource Plan | 7 | 40 | 280 | - | - | - | 280 |  | 280
2.4 Project Scheduling | 12 | 40 | 480 | - | - | - | 480 |  | 480
2.5 Risk management plan | 8 | 40 | 320 | - | - | - | 320 |  | 320
3. Design phase | [8 empty] | 0
3.1 Design UI | 20 | 40 | 800 | - | - | - | 800 |  | 800
3.2 Learning of PHP | 16 | 40 | 640 | - | - | - | 640 |  | 640
3.3 Design database | 20 | 40 | 800 | - | - | - | 800 |  | 800
4. Testing phase | [8 empty] | 0
4.1 Test UI design | 16 | 40 | 640 | - | - | - | 640 |  | 640
4.2 Test backend | 14 | 40 | 560 | - | - | - | 560 |  | 560
5. Presentation phase |  | 40 | 0 | - | - | - | 0 |  | 0
5.1 Prepare video for presentation | 10 | 40 | 400 | - | - | - | 400 |  | 400
5.2 Rehearse for presentation | 5 | 40 | 200 | - | - | - | 200 |  | 200
Subtotal |  |  | 8400 |  |  |  | 8400 |  | 8400
Reserves
Total | [8 empty] | SGD$8,400