## Sheet1
Risk Register for Covid - 05
Date: 13 April 2020
Project Name: |  | Room Booking System Prototype
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 1 | Some team members lack of programming experience | Technological risk | Split the team into 2 separate groups. One team to be in charge of documentation and the other in programming. | Decen Ng | H | H | L - The work is split evenly according to each member's capabilities
2 | 4 | File corruption/system failures | Technological risk | Sharing/Backing up the files | Jing Jue Ching | L | H | L - Every member has a copy of the project to provide file backup.
3 | 5 | Design , interface and maintenance issues | Technological risk | Perform test to ensure system runs efficiently and in the desired manner | Jing Xian Ching | M | H | M - Could still have unexpected or unforeseen issues/bugs
4 | 2 | Communication breakdown | Personnel risk | Engage in team bonding games to get to know each other bettter | Neo Kai Heng | M | M | M - Once team members gets to know each other better, communication breakdown is less likely to occur and team becomes more efficient.
5 | 3 | Unable to meet the given deadlines | Schedule risk | Follow up and update on schedule, minutes | Seri Dania | M | H | L - As long as schedule is followed closely by all team members, it is highly unlikely for us to miss any key deadlines.
6 | 6 | Escalation of cost | Cost risk | Propose realistic budget plan | Junior Tantono | M | H | L - With a realistic budget plan, exceeding the budget is unlikely to occur unless due to unforseen circumstances.
7 | 7 | Plagiarism by other groups | Administrative risk | Avoid sharing our project contents with anyone outside of our group | Junior Tantono | L | H | L - As long as we do not share our contents, no other teams will be able to access it.